## Product backlog
PRODUCT BACKLOG
Backlog ID | Actor | Epics | Backlog items | User story | Categogy | Effort | Priority | Sprint # | Acceptance Criteria | Status
PB_01 | Admin | Login/Logout Admin | Login/Logout with Admin VLU's mail | As an Admin, I want to login/logout to the system | Feature | 2 | Low | 3 | AC1: * Admin login into website using Admin's VLU email and being redirect to homepage after login verification succeeded AC2: * If User logged in by using mail other than Admin's email, website will redirect to login page with error message AC3: * The system redirects to the login page after faculty click logout button and faculty can't be able to access any Admin features. AC4: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_02 | Admin | User Management | View list of Users | As an Admin, I want to see the list of accounts registered into the system | Feature | 3 | Low | 3 | AC1: * Admin can View list of user accounts registered into the system AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed. | Open
PB_03 |  |  | Authorize user | As an Admin, I want to authorize user's account | Feature | 3 | Low | 3 | AC1: * Admin can authorize user's account AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed. | Open
PB_04 |  |  | Delete user | As an Admin, I want to delete user's account | Feature | 2 | Low | 3 | AC1: * Admin can Delete a user's account in the system AC2; * Website will show confirmation message and Admin has to confirm before it actually delete AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_05 | Faculty | Login/Logout Faculty | Login/Logout with Faculty's VLU mail | As a Faculty, I want to login/logout to the system with faculty VLU's email | Feature | 2 | High | 1 | AC1: * Faculty login into website using faculty's VLU email and being redirect to homepage after login verification succeeded AC2: * If User logged in by using mail other than faculty's email, website will redirect to login page with error message AC3: * The system redirects to the login page after faculty click logout button and faculty can't be able to access any Faculty features. AC4: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_06 | Faculty | Study Program Management | Import study program | As a Faculty, I want to import the study program of the student into system | Feature | 13 | High | 1 | AC1: * Faculty can import study program of the student into system AC2: * System will display error if Faculty hasn't import file but click on import button or import wrong file format AC3: * System will display error if the file is missing columns AC4: * System displays waiting message when system is importing file AC5: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_07 |  |  | View study program | As a Faculty, I want to view study program base on major and course | Feature | 8 | High | 1 | AC1: * Faculty can view study program base on major and course in the system AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_08 | Faculty | Study Results Management | Import study results | As a Faculty, I want to import the study results of student into the system | Feature | 8 | High | 2 | AC1: * Faculty can import study results of the student into system AC2: * System will display error if Faculty hasn't import file but click on import button or import wrong file format AC3: * System will display error if the file is missing columns AC4: * System displays waiting message when system is importing file AC5: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_09 |  |  | View study results | As a Faculty, I want to view study results of a student base on student's ID | Feature | 5 | High | 2 | AC1: * Faculty can view study results of a student base on student's ID AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_10 |  |  | Search student study results | As a Faculty, I want to search students to view their study results in case I don't know student't ID | Feature | 5 | Medium | 2 | AC1: * Faculty can search students to view their study results in case faculty doesn't know student't ID AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_11 | Faculty | Registration Results Management | Import registration results | As a Faculty, I want to import the registration results of student into the system | Feature | 8 | High | 2 | AC1: * Faculty can import registration results of the student into system AC2: * System will display error if Faculty hasn't import file but click on import button or import wrong file format AC3: * System will display error if the file is missing columns AC4: * System displays waiting message when system is importing file AC5: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_12 |  |  | View registration results | As a Faculty, I want to view registration results of a student base on student's ID | Feature | 5 | High | 2 | AC1: * Faculty can view registration results of a student base on student's ID AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_13 |  |  | Search student registration results | As a Faculty, I want to search student to view their registration results in case I don't know student't ID | Feature | 5 | Medium | 2 | AC1: * Faculty can search students to view their registration results in case faculty doesn't know student't ID AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passe | Open
PB_14 | Faculty | Student Course Management | View List of student course | As a Faculty, I want to view list of student course | Feature | 3 | High | 1 | AC1: * Faculty can view the list of student course AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_15 |  |  | Create student course | As a Faculty, I want to create a new student course | Feature | 3 | High | 1 | AC1: * Faculty can create a new student course AC2: * If some of the fields have not been filled or wrong format, website will show error at that field AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_16 |  |  | Update student course | As a Faculty, I want to update a student course | Feature | 3 | High | 1 | AC1: * Admin can Update a student course AC2: * If some of the fields have not been filled or wrong format, website will show error at that field AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed. | Open
PB_17 |  |  | Delete student course | As a Faculty, I want to delete a student course | Feature | 3 | High | 1 | AC1: * Faculty can Delete a student course AC2; * Website will show confirmation message and Faculty has to confirm before it actually delete AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_18 |  |  | Search student course | As a Faculty, I want to search student course | Feature | 3 | Medium | 1 | AC1: * Faculty can search student course AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_19 | Faculty | Major Management | View List of majors | As a Faculty, I want to view list of majors | Feature | 3 | High | 1 | AC1: * Faculty can view the list of majors AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_20 |  |  | Create major | As a Faculty, I want to create a new major | Feature | 3 | High | 1 | AC1: * Faculty can create a new major AC2: * If some of the fields have not been filled or wrong format, website will show error at that field AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_21 |  |  | Update major | As a Faculty, I want to update a major | Feature | 3 | High | 1 | AC1: * Admin can Update a major AC2: * If some of the fields have not been filled or wrong format, website will show error at that field AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed. | Open
PB_22 |  |  | Delete major | As a Faculty, I want to delete a major | Feature | 3 | High | 1 | AC1: * Faculty can Delete a major AC2; * Website will show confirmation message and Faculty has to confirm before it actually delete AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_23 |  |  | Search majors | As a Faculty, I want to search majors | Feature | 3 | Medium | 1 | AC1: * Faculty can search majors AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_24 | Faculty | Student Progress Statistics | View statistics about student progress | As a Faculty, I want to view statistics about student progress | Feature | 5 | Low | 3 | AC1: * Faculty can view statistics about student progress to see how many students are on the right progress, how many students aren't AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed. | Open
PB_25 | Faculty |  | View list of students in statistics | As a Faculty, I want to view list of students that have been counted in statistics | Feature | 5 | Low | 3 | AC1: * Faculty can view list of students that have been counted in statistics, to know who is on the right progress and who isn't AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed. | Open
PB_26 | Student | Login/Logout Student | Login/Logout with Student's VLU mail | As a Student, I want to login/logout to the system with Student VLU's email | Feature | 2 | High | 2 | AC1: * Faculty login into website using lecturer's VLU email and being redirect to homepage after login verification succeeded AC2: * If User logged in by using mail domain other than "vanlanguni.vn", website will redirect to login page with error message AC3: * The system redirects to the login page after faculty click logout button and faculty can't be able to access any Faculty features. AC4: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_27 | Student | Learning Progress Management | View Learning Progress | As a Student, I want to see learning progress of myself, to see which subjects I passed, and which subjects I failed | Feature | 8 | High | 2 | AC1: * Student can view their learning progress based on student's id AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_28 |  |  | View statistics about learning progress | As a Student, I want to view statistics about their learning progress | Feature | 5 | Low | 3 | AC1: * Student can view statistics about their learning progress, to see how many subjects they have passed, how many subjects they have failed,.. AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_29 | Student | Study Plan Management | View list of available study plan | As a Student, I want to see the list of available study plan that I can register | Feature | 3 | Medium | 3 | AC1: + Student can view list of available study plan AC2: + Website will show "Hiện tại không có kế hoạch học tập nào dành cho bạn" message if there's no available study plan AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_30 |  |  | Register Personal study plan | As a Student, I want to register for my personal study plan | Feature | 5 | Medium | 3 | AC1: * Student can register new personal study plan on View list of available study plan AC2: * Website will show "Bạn đã đăng ký kế hoạch học tập cho môn … thành công" message if student register successfully AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_31 |  |  | View list of registered study plan | As a Student, I want to see the list of study plan that I have registered | Feature | 3 | Medium | 3 | AC1: + Student can view list of registered study plan AC2: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
PB_32 |  |  | Delete registered study plan | As a Student, I want to delete registered study plan | Feature | 3 | Medium | 3 | AC1: * Student can delete registered study plan AC2: * Website will show confirmation message and Faculty has to confirm before it actually delete AC3: Document Testing Passed + Function Test: Passed + Integration Test: Passed | Open
Effort of each Sprint
[7 empty] | Sprint | Effort
[7 empty] | 1 | 53
[7 empty] | 2 | 46
[7 empty] | 3 | 39
[7 empty] | Total | 138